## Sheet1
Description | Who | 6th Feb | 13th Feb | 20th Feb | 27th Feb | 6th Mar | 13th Mar | 20th Mar | 27th Mar | 3rd Apr | 10th Apr | 17th Apr | 24th Apr | 1st May
Project Revew
Formal Review Meeting - dates, deliverables and budget | HA/AF/FH/CY
Servers and Infrastructure
Production set up | AF/HC
Update Process | IC
User Interface Dev
Dev | AF
User Names | AF
Use Test & Feed Back | FH
Dev Update and Release | AF
Documentation | AF
Test Access for Users | AF
Requirements and Queries
Decide Rules Order | FH
Support Process and Structure | HC
Rule 1
UAT | FH/AF
Live - Glasgow | FH
Roll Out | FH
Rule 2
Set Up | AF
UAT | FH/AF
Live - Glasgow | FH
Roll Out | FH
Rule 3
Set Up | AF
UAT | FH/AF
Live - Glasgow | FH
Roll Out | FH
Rule 4
Set Up | AF
UAT | FH/AF
Live - Glasgow | FH
Roll Out | FH
Rule 5
Set Up | AF
UAT | FH/AF
Live - Glasgow | FH
Roll Out | FH
Rule 6
Set Up | AF
UAT | FH/AF
Live - Glasgow | FH
Roll Out | FH
Dashboard Development
Review of Options | AF/MF
Outline Dev Plan | AF/MF
Proof of Concept | AF/MF
Development of Fist Stage Reports | AF/MF